## Sheet1
Date Received/DRC | Date amended | Plan # | Plan Name | Type | Details | Decision | Reasoning | Prior Precendent | Response Date | Response Method
2012-10-02 |  |  | 4916 Elm Street |  | Request for retaining wall and non-standard sidewalk section in the right-of-way to result in a more level seating café seating area | Conditional Approval | subject to providing 2’ minimum level area behind the curb to facilitate access to parked cars |  | 2012-10-25 | email to DPS, Bethesda Urban Partnership, and consultant
2012-06-11 |  | 120120220 | 7001 Arlington Road | Sight Distance | Sight distances issue at southern entrance affects egress movements | Conditional Approval | of applicant’s Traffic Signal Warrant study subject to acquisition of necessary easements and address need to restripe opposite parking lot |  | 2012-09-25 | plan review letter to P&P and applicants
2012-06-11 |  | 120120220 | 7001 Arlington Road |  | Postpone reconstruction of Arlington Road site frontage (per Sector Plan) | Conditional Approval | subject to execution and recordation of road construction covenant for permanent frontage improvements |  | 2012-09-25 | plan review letter to P&P and applicants
2012-05-21 | 2012-12-12 | 120120200 | 7900 Wisconsin Avenue |  | Proposed driveway locations and reduced spacing [per DTEO policy] | Conditional Approval | in consideration of CBD location |  | 2013-01-24 | plan review letter to P&P and applicants
2012-05-21 | 2012-12-12 | 120120200 | 7900 Wisconsin Avenue |  | Reduction in the number of off-street truck loading spaces [from that required by Executive Branch policy] | Conditional Approval | subject to execution and recordation of a County-approved Restricted Access Easement which establishes the applicability, maintenance, and operations of the coordinated on-site management for the jointly used loading docks and provision for an on-site oversized WB-50 truck loading space (which can be used to accommodate 2 SU-30 trucks) |  | 2013-01-24 | plan review letter to P&P and applicants
2016-01-11 |  | 120160050 | 8008 Wisconsin Avenue | Driveway Spacing | reduced spacing along Cordell Avenue | Conditional Approval | 100 foot cannot be met due to short distance between Wisconsin and Woodmont |  | 2016-06-24
2016-01-11 |  | 120160050 | 8008 Wisconsin Avenue | Loading | reduced loading | Conditional Approval | meets current zoning ordinance requirements |  | 2016-06-24
2016-04-04 |  | 120160220 | 8015 Old Georgetown Road | Driveway Spacing | less than 100 feet from Old Georgetown Road | Conditional approval | 100 foot cannot be met due to short distance between Old Georgetown and property line |  | 2016-07-29 | Plan review letter to P&P and applicants
2016-04-04 |  | 120160220 | 8015 Old Georgetown Road | Roadway Modification | Rugby cul-de-sac is 45 foot diameter | Conditional Approval | emergency vehicles can use alternative path; SU-30 trucks can turn around |  | 2016-07-29
2016-04-04 |  | 120160220 | 8015 Old Georgetown Road | Loading | reduction in number of loading spaces | Conditional Approval | meets current zoning ordinance requirements |  | 2016-07-29
2016-10-17 |  | 120170070 | 8912 Liberty Lane | Roadway Modification | relief from providing shoulder, side ditch, and street trees | conditional approval | needs a declaration of covenants |  | 2017-05-05 | plan review letter to P&P and applicants
2011-04-11 | 2012-01-24 | 120070750 | Alta Vista – ACC [American College of Cardiologists] | SWM | Stormwater Management Measures in the rights-of-way on Camberley Avenue Extended | Conditional Approval | of MSHA flume inlets and water quality/bio-swales on closed section roads and reduce the maintenance panel width to 1’ |  | 2012-05-24 | plan review comments letter to P&P and applicants
2011-04-11 | 2012-01-24 | 120070750 | Alta Vista – ACC [American College of Cardiologists] |  | Request to waive sidewalk on the north side of Camberley Avenue Extended | Conditional Approval | to facilitate installation of proposed stormwater management measures subject to DPS approval of Waiver & Fee Payment, providing rear access to HOA property from affected lots, etc. |  | 2012-05-24 | plan review comments letter to P&P and applicants
2011-04-11 | 2012-01-24 | 120070750 | Alta Vista – ACC [American College of Cardiologists] |  | Increase in lots accessing a private driveway [from that allowed by unwritten DOT policy] | Conditional Approval | subject to execution and recordation of reciprocal access, utilities, and maintenance agreement, references same on the record plat, confirmation of maintenance cost calculations, and discloses of parking restrictions |  | 2012-05-24 | plan review comments letter to P&P and applicants
2011-04-11 | 2012-01-24 | 120070750 | Alta Vista – ACC [American College of Cardiologists] |  | Applicant appeal of the Camberley Avenue Extended typical section comments in our 5/24/12 plan review letter | Conditional Approval | to allow 28’ pavement section with stormwater management |  | 2012-06-08 | amended plan review letter to P&P and applicants
2015-12-28 |  | 12007020B | Artery Plaza | Driveway Spacing |  | Conditional Approval |  |  | 2016-02-29 | plan review letter to P&P and applicants
2015-12-28 |  | 12007020B | Artery Plaza | other | Amenity Space (Outdoor Café Seating) in the pblic-right-of-way | Conditional Approval | Approved subject to DPS Outdoor Café Seating Guidelines. |  | 2016-02-29 | plan review letter to P&P and applicants
2011-10-17 | 2011-11-14 | 120120070 | Bethesda Center |  | Proposed driveway locations and reduced spacing [per DTEO policy] | Conditional Approval | in consideration of CBD location, with channelized southern (combined truck and parking garage egress) driveway to preclude westbound left turn movements (& conflicts with exits from adjacent existing driveway) |  | 2011-11-29 | plan review comments letter to P&P and applicants
2011-10-17 | 2011-11-14 | 120120070 | Bethesda Center |  | Request to remove existing metered parking spaces to create private layby on Woodmont Avenue site frontage | Denied | during plan review; applicant subsequently incorporated a private drop-off area on-site |  |  | Deleted from plan following Sept 2011 meetings with applicant, Parking Management, etc
2017-08-31 |  | 120170150 | Bloom MV | Roadway Modification | modification to context sensitive road sections for proposed Stewartown Road | Conditional Approval | Modified Roadway cross section based on the masterplan |  | 2017-09-26 | plan review letter to P&P and applicants
2017-08-31 |  | 120170150 | Bloom MV | other | Modified Monumental Entrance | Conditional Approval | Reduced monumental entrance lengths per the master plan & the proposed roadway anticipated to function like an Secondary Residential Road |  | 2017-09-26 | plan review letter to P&P and applicants
2011-02-28 | 2011-06-03 | 120110120 | Bowie Mill Propert |  | Modified business district street typical section on internal residential streets | Conditional Approval | to provide 28’ closed section street with parking and reduce the maintenance panel width to 1’ |  | 2011-06-17 | plan review comments letter to P&P and applicants
2011-02-28 | 2011-06-03 | 120110120 | Bowie Mill Propert | SWM | Stormwater Management Measures in the rights-of-way of internal residential streets | Conditional Approval | MSHA flume inlets and water quality/bio-swales on closed section roads on a pilot basis |  | 2011-06-17 | plan review comments letter to P&P and applicants
2011-02-28 | 2011-06-03 | 120110120 | Bowie Mill Propert | Sidewalk | Eliminate sidewalk on one side of the proposed internal residential streets | Denied | due to planned development on both sides of the streets |  | 2011-06-17 | plan review comments letter to P&P and applicants
2016-09-19 |  | 120170060 | Bradford's Landing | Roadway Modification | incorporate an 8' hiker/biker trail & 5' sidewalk in a 44' tertiary road R/W (std MC-2001.01) | Conditional Approval | requested by the Planning Dept, to provide regional access to a proposed internal park - NOT TO SET A PRECEDENT | No | 2016-11-14 | prelim plan letter
2016-09-19 |  | 120170060 | Bradford's Landing | Roadway Modification | change 5' sidewalk to an 8' hiker/biker trail, retain other 5' sidewalk, & add parallel parking in a 50' tertiary road R/W (std MC-2001.02) | Conditional Approval | requested by the Planning Dept, to provide ped/bike regional access and parking for a proposed internal park - NOT TO SET A PRECEDENT. NOTE: our 11/23/16 Amendment Letter stated: On-street parking will NOT be allowed if the pavement width is less than 28 feet wide, curb-to-curb. It also indicated the 5' wide sidewalk may be located adjacent to the curb where this on-street parking; where will be no designated on-street parking, the sidewalk is to be set back from the curb by a 4 foot (minimum width) lawn panel planted with minor species street trees. A 2' Public Improvements Easement may be needed if the sidewalk falls outside the right-of-way. | No | 2016-11-14 | prelim plan letter
2016-09-19 |  | 120170060 | Bradford's Landing | Roadway Modification | change 5' sidewalk to an 8' hiker/biker trail, retain other 5' sidewalk, & replace designated parking on one side with lawn panel in a 60' tertiary road R/W (std MC-2002.02) | Conditional Approval |  |  | 2016-11-14 | prelim plan letter
2016-09-19 |  | 120170060 | Bradford's Landing | Roadway Modification | widen the pavement to 36' in a 60' secondary residential road R/W (std MC-2003.11) | Conditional Approval | approved subject to MDSHA approval at the intersection with MD28 |  | 2016-11-14 | prelim plan letter
2016-09-19 |  | 120170060 | Bradford's Landing | Roadway Modification | Allow superelevation on MINIMAL tangent sections of tertiary roads (stds MC-2001.01 & 2001.02) | Conditional Approval | needed to connect with horizontal curve on an existing side street and minimize impact on nearby existing residential development | No | 2016-11-14 | prelim plan letter
2016-09-19 |  | 120170060 | Bradford's Landing | Sidewalk | allow surface grates to cross the proposed sidewalks (perpendicular to the direction of travel) | Conditional Approval | the grates are needed to meet stormwater management requirements. Applicant must execute and record a M&L Agreement for maintenance (w/deed reference on the plat), prior to issuance of the R/W construction permit. | No | 2016-11-14 | prelim plan letter
2016-09-19 |  | 120170060 | Bradford's Landing | Roadway Modification | reduce the pavement width from 26' to 21.5' on secondary residential road R/W (std MC-2002.01) | Conditional Approval | the proposed modification ties into the areas of proposed on-street parking better and provides a traffic calming benefit at the proposed intersections |  | 2016-11-14 | prelim plan letter
2011-07-25 |  | 120110370 | Bradley Farms |  | Applicant appeal of the Durham Drive roadway improvement comments in our 8/19/11 plan review letter | Conditional Approval | to widen road now between their driveway and River Road (MD 190); balance of site frontage covered by recorded road construction covenant |  | 2011-12-30 | amendment letter to P&P and applicant
2014-10-24 |  | 12003110A | Cabin Branch-Gosnell Farm Drive | Median Break | Median Break waiver on Gosnell Farm Drive | Conditional Approval
2011-03-22 |  | G-892 | Chelsea Court |  | Proposed private intersection spacing on Springvale Road [per DTEO policy] | Conditional Approval | subject to providing channelization at the private street intersection – to limit vehicle turning movements to right in/right out, reinforce existing traffic restrictions, and address driver expectancies at the nearby intersection with Pershing Drive |  | 2012-03-23 | email to P&P and applicants
2016-09-06 |  | 12002020B | Chevy Chase Lake Block B | Sidewalk | scored concrete in ROW | conditional approval | applicant will provide an M&L agreement |  | 2017-04-28 | plan review letter to P&P and applicants
2016-09-06 |  | 12002020B | Chevy Chase Lake Block B | Sidewalk | structures in ROW | conditional approval | applicant will provide an M&L agreement; Bill 34-16 |  | 2017-04-28 | Plan review letter to P&P and applicants
2016-02-09 |  | 11995042C | Clarksburg Town Center | Driveway Spacing | Channelized Entrance with right-in only turn | Conditional Approval |  |  | 2016-03-04 | plan review letter to P&P and applicants
2011-06-06 |  |  | Clarksburg Village | SWM | Stormwater Management Measures in the right-of-way for A-302 (Little Seneca Parkway) | Conditional Approval | MSHA flume inlets and trapezoidal ditches on the closed section road |  | 2011-06-29 | email to consultant and DPS Water Resources
2014-11-24 |  | 120140240 | East Village at North Bethesda | Radii | driveway radii reduced to 10 feet | conditional approval | operations for loading would meet County standards |  | 2016-08-26 | plan review letter to P&P and applicants
2014-11-24 |  | 12040240 | East Village at North Bethesda | Driveway Spacing | spacing from existing driveway along Huff Court | conditional approval | meets county sight distance requirements; also applicant should work with adjacent property owner when they redevelop |  | 2016-08-26 | plan review letter to P&P and applicants
2014-11-24 |  | 120140240 | East Village at North Bethesda | Loading | reduction in number of loading spaces | conditional approval | meets current zoning ordinance requirements |  | 2016-08-26 | plan review letter to P&P and applicants
2014-11-24 |  | 120140240 | East Village at North Bethesda | Sidewalk | special paving for sidewalks in the ROW | conditional approval | needs a maintenance and liabliity agreement |  | 2016-08-26 | plan review letter to P&P and applicants
2014-11-24 |  | 120140240 | East Village at North Bethesda | Roadway Modification | modification to context sensitive road sections for Nicholson Lane and Huff Court | conditional approval | Nicholson Lane to comply with cycle track and huff Court to provide an urban environment as envisioned in the MP |  | 2016-08-26 | Plan review letter to P&P and applicants
2014-11-24 |  | 120140240 | East Village at North Bethesda | Roadway Modification | layby on Huff Court | conditional approval | restricted for "no parking any time" |  | 2016-08-26 | Plan review letter to P&P and applicants
2015-05-23 |  | 120150030 | Elizabeth Square | Roadway Modification | Fenwick lane & Apple Avenue -Reduce pavement width | Conditional Approval | Reduced pavement width per Bill 33-13 |  | 2015-06-16 | Preliminary plan Letter
2015-05-23 |  | 120150030 | Elizabeth Square | other | Reduced right-of-way width | Conditional Approval | Reduce right-of-way from 60-ft to 50-ft. |  | 2015-06-16 | Preliminary plan Letter
2015-05-23 |  | 120150030 | Elizabeth Square | Driveway Spacing | waiver from 100' tangent | Conditional Approval | space limitations due to urban area |  | 2015-06-16 | Preliminary plan Letter
2015-05-23 |  | 120150030 | Elizabeth Square | other | Place obstructions like SWM Facility, Electrical Facility, Collapsible Bollards, Bicycle Rack, Grasscrete for Fire Access, Standard County Freestanding Facility Sign within the right-of-way | Conditional Approval | space limitations due to urban area |  | 2015-06-16 | Preliminary plan Letter
2015-05-23 |  | 120150030 | Elizabeth Square | other | Non standard cul-de-sac - Offset cul-de-sac, Reduce right-of-way radius & outside radius | Conditional Approval |  |  | 2015-06-16 | Preliminary plan Letter
2015-05-23 |  | 120150030 | Elizabeth Square | Radii | Reduce curb radii | Conditional Approval | per Bill 33-13 |  | 2015-06-16 | Preliminary plan Letter
2011-09-12 | 2011-09-12 | 120110400 | Fenwick Station | Sight Distance | Insufficient sight distances from proposed entrance to underground garage on Fenwick Lane | Conditional Approval | work with the Division of Parking Management to relocate several existing metered parking spaces on Second Avenue (where the applicant was proposing to close several existing driveways) |  | 2011-09-30 | plan review comments letter to P&P and applicants
2010-06-14 | 2011-03-23 | 120100250 | First Baptist Church of Wheaton | Roadway Modification | Modified typical section across the Emory Church Road | Conditional Approval | to eliminate the standard side ditch while promoting overland flow to existing drainage course of private property, and allow the sidewalk to meander around existing trees, etc – to minimize environmental impact |  | 2011-06-28 | plan review comments letter to P&P and applicants
2012-04-09 | 2012-03-06 | 120120150 | Goddard School - Olney | SWM | Applicant appeal of proposed superelevated alley typical section comments in our 8/1/12 plan review letter | Conditional Approval | to better achieve stormwater management quality goals on low volume, low speed access road |  | 2012-10-12 | amended plan review letter
2015-12-22 | 2016-04-25 | 120150110 | Hannibal Farms | Roadway Modification | Request to Deviate from Roadway Design Standard MC-2001.03 (Tertiary Residential Street-Open Section) roadway cross section to fit within the 60-ft for proposed Hannibal Way and Hannibal Court. | Conditional Approval |  |  | 2016-05-11 | Amended Preliminary Plan Letter
2010-01-19 | 2012-04-16 | 120100130 | ISG [Islamic Society of Germantown] Property | other | Applicant appeal of the Blunt Road roadway improvement comments in our 12/2/11 plan review letter | Conditional Approval | of modified temporary typical section and road improvement, subject to execution and recordation of road construction covenant for permanent frontage improvements |  | 2012-04-28 | amended plan review letter to P&P and applicants
2011-04-11 | 2011-06-03 | 11996110A | Johns Hopkins Belward Campus | SWM | Stormwater Management Measures in the rights-of-way on internal public business district streets | Conditional Approval | MSHA flume inlets and water quality/bio-swales on closed section roads and reduce the maintenance panel width to 1’ |  | 2011-06-17 | plan review comments letter to P&P and applicants
2011-04-11 | 2011-06-03 | 11996110A | Johns Hopkins Belward Campus | SWM | Stormwater Management Measures in the rights-of-way on internal public business district streets | Denied | to install structural, rectangular boxes on Belward Campus Drive due to safety and liability concerns |  | 2011-06-17 | plan review comments letter to P&P and applicants
2011-04-11 | 2011-06-03 | 11996110A | Johns Hopkins Belward Campus |  | Request to have Master Planned roads B-3 and B-4 be privately owned and maintained | Conditional approval recommendation (to planning board) | subject to a recorded perpetual Public Access Easement document |  | 2011-06-17 | plan review comments letter to P&P and applicants
2011-03-21 | 2011-09-12 | 11986115C | Johns Hopkins Montgomery Medical Center Campus |  | Request to have Master Planned roads B-7, B-8 and B-11 be privately owned and maintained | Conditional approval recommendation (to planning board) | subject to a recorded perpetual Public Access Easement document & other details |  | 2011-10-06 | plan review comments letter to P&P and applicants
2011-03-21 | 2011-09-12 |  | Johns Hopkins Montgomery Medical Center Campus | SWM | Stormwater Management Measures in the rights-of-way on internal public business district streets | Conditional Approval | MSHA flume inlets and water quality/bio-swales on closed section roads and reduce the maintenance panel width to 1’ |  | 2011-10-06 | plan review comments letter to P&P and applicants | 2013-01-18 | follow-up email to DPS, P&P, and applicants
2011-03-21 | 2011-09-12 |  | Johns Hopkins Montgomery Medical Center Campus | SWM | Stormwater Management Measures in the rights-of-way on internal public business district streets | Denied | of request to install structural, rectangular boxes on Belward Campus Drive due to safety and liability concerns |  | 2011-10-06 | plan review comments letter to P&P and applicants
2010-01-19 |  | 120100100 | Little Bennett Creek | Roadway Modification | Modified typical section for Kings Valley Road site frontage to delete sidewalk construction by this applicant | Conditional Approval | based on 1/18/13 email from Bill Gries confirming P&P Parks’ desire to accept proposed dedication and grading of shelf for sidewalk installation (if needed in the future) |  | 2013-01-29 | plan review letter to P&P and applicant
2005-10-11 |  | 120060330 | Marian Fathers | Radii | reduce curb return radii from 30 to 25 feet | Conditional Approval | consistent with recent changes to curb return radii requirements in Bill 33-13 |  | 2014-12-17 | plan review letter
2009-06-01 |  | 120060330 | Marian Fathers | SWM | construct bio-swales in ROW | conditional approval | consistent with context sensitive road design standards |  | 2014-12-17 | prelim plan letter
2009-06-01 |  | 120060330 | Marian Fathers | Sidewalk | not to construct sidewalk on one side of street | Conditional Approval | consistent with bill 33-13 |  | 2014-12-17 | prelim plan letter
2017-10-10 |  | 120180020 | Marriott Headquarters | Driveway Spacing | waiver from 100' tangent | Conditional Approval |  |  | 2017-11-06 | plan review letter to P&P and applicants
2011-05-17 |  | 120110090 | Martens Property | SWM | Stormwater Management Measures in the rights-of-way for Waterford Hills Boulevard and Waters Road | Conditional Approval | MSHA flume inlets, water quality/bio-swales and Filterra structures on the closed section roads on a pilot basis |  | 2011-07-29 | email to DPS Water Resources and P&P
2011-07-25 | 2011-10-10 | 120110090 | Martens Property |  | Proposed median break locations [from DTEO spacing policy] | Conditional Approval | based on Vehicle Queueing Analysis from applicant’s traffic consultant |  | 2011-11-14 | plan review comments letter to P&P and applicants
2011-07-25 | 2011-10-10 | 120110090 | Martens Property |  | Modified typical sections on Waterford Hills Boulevard and Waters Road | Conditional Approval | to accommodate stormwater management and other context sensitive design measures |  | 2011-11-14 | plan review comments letter to P&P and applicants
2011-07-25 | 2011-10-10 | 120110090 | Martens Property | SWM | Stormwater Management Measures in the rights-of-way on Waterford Hills Boulevard and Waters Road | Conditional Approval | MSHA flume inlets, water quality/bio-swales and Filterra structures |  | 2011-11-14 | plan review comments letter to P&P and applicants
2011-07-25 | 2011-10-10 | 120110090 | Martens Property | SWM | Proposal to provide stormwater management measures within the median for Waterford Hills Boulevard | Denied | due to concerns over traffic safety and operations |  | 2011-11-14 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Reverse grading of parking lanes and varying of sidewalk/parking lane slope | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement |  | 2012-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Retaining walls and stairs in the public rights-of-way | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement |  | 2011-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Right-of-way truncation to 0” (for CR zone) at intersections with MD 187 | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement |  | 2011-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Intersection radii reduction to 25’ | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement |  | 2011-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Silva Cells and structural filtration in the public right-of-way, trench drains along the curb | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement {SWM concept was also conditionally approved in 1/19/12 email to DPS Water Resources and applicants) |  | 2011-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Reduced travel lane width of Streets “A” and “I” | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement |  | 2011-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | New dry utilities within the right-of-way | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement [11/15/11 amended utility concept plan reduced the number of dry utility installations in County rights-of-way] |  | 2011-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Reduction in the number of off-street truck loading spaces [from that required by Executive Branch policy | Conditional Approval | subject to execution and recordation of a County-approved Restricted Access Easement which establishes the applicability, maintenance, and operations of the coordinated on-site management for the jointly used loading docks |  | 2011-01-25 | plan review comments letter to P&P and applicants
2011-09-06 | 2011-12-07 | 120120020 | Mid Pike Plaza |  | Special Pavement at the intersection of Streets “A” & “2” | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement |  | 2011-01-25 | plan review comments letter to P&P and applicants
2015-11-12 | 2016-03-25 | 11985027A | Montgomery Auto Sales, Lot 14 | Driveway Spacing | Due to the close proximity of the existing driveway less than 100-ft. | Conditional Approval |  |  | 2016-04-01 | Amended Preliminary Plan Letter
2011-09-26 | 2012-11-18 | 120120060 | North Bethesda Markett II |  | Steps in the right-of-way at the southeast corner of the intersection of Nicholson Lane and Woodglen Drive | Conditional Approval | subject to providing more detail at the permit stage which affirms adequate separation between the steps, pedestrians, signal system, etc. |  | 2012-02-03 | plan review comments letter to P&P and applicants
2011-09-26 | 2012-11-18 | 120120060 | North Bethesda Markett II |  | Proposed driveway locations and reduced spacing on Woodglen Drive and Executive Boulevard [per DTEO policy] | Conditional Approval | in consideration of CBD location |  | 2012-02-03 | plan review comments letter to P&P and applicants
2011-09-26 | 2012-11-18 | 120120060 | North Bethesda Markett II |  | Reduction in the number of off-street truck loading spaces [from that required by Executive Branch policy] | Conditional Approval | subject to execution and recordation of a County-approved Restricted Access Easement which establishes the applicability, maintenance, and operations of the coordinated on-site management for the jointly used loading docks |  | 2012-02-03 | plan review comments letter to P&P and applicants
2011-05-23 | 2011-06-06 | 120110300 | Parklawn North | SWM | Stormwater Management Measures in the rights-of-way on Wilkens Avenue Extended | Conditional Approval | use Silva Cells on a pilot basis |  | 2011-06-18 | plan review comments letter to P&P and applicant
2011-05-23 | 2011-06-06 | 120110300 | Parklawn North | Driveway Spacing | Driveway location spacings | Conditional Approval | based on Vehicle Queueing Analysis from applicant’s traffic consultant |  | 2011-06-18 | plan review comments letter to P&P and applicant
2011-05-23 | 2011-06-06 | 120110300 | Parklawn North |  | Modified business district street typical section on Wilkens Avenue Extended | Conditional Approval | to add 8’ shared use path by reducing the maintenance panel width to 1’ |  | 2011-06-18 | plan review comments letter to P&P and applicant
2011-05-23 | 2011-06-06 | 120110300 | Parklawn North |  | Perpendicular parking within the right-of-way of Wilkens Avenue Extended | Denied |  |  | 2011-06-18 | plan review comments letter to P&P and applicant
2011-05-23 | 2011-06-06 | 120110300 | Parklawn North |  | Installation of underground electric line at the intersection of Fishers Lane and Wilkens Avenue Extended | Denied | did not receive an alternatives analysis from the consultant (that demonstrated it would not be feasible to locate same on private property) |  | 2011-06-18 | plan review comments letter to P&P and applicant
2013-01-31 |  | 12012002A 820130120 | Pike & Rose (Mid Pike Plaza) |  | Request to install a layby in front of proposed hotel | Denied | per Al Roshdieh’s message |  | 2013-02-07 | ARR email to applicant
2016-09-06 |  | 120120010 | Ridgeview | Roadway Modification | Roadway cross section & Sidewalk on one side | Conditional Approval | proposed reduced right-of-way and environmental concerns per the master plan. |  | 2017-04-18
2015-11-09 |  | 120160080 | Saul Centers at White Flint | Driveway Spacing | loading bay is less than 100 feet from Marinelli and Private drive A | conditional approval | not possible due to distance between Marinelli and Private Drive A |  | 2016-05-05
2015-11-09 |  | 120160080 | Saul Centers at White Flint | Loading | reduction in number and size of loading spaces | Conditional Approval | meets current zoning ordinance requirements |  | 2016-05-05
2015-11-09 |  | 120160080 | Saul Centers at White Flint | Sidewalk | special paving for sidewalks in the ROW | conditional approval | needs a maintenance and liabliity agreement |  | 2016-05-05
2015-11-09 |  | 120160080 | Saul Centers at White Flint | Roadway Modification | modify street section for Woodglen Drive extended | Conditional Approval | modification was recommended at sketch plan by DOT |  | 2016-05-05
2015-11-09 |  | 120160080 | Saul Centers at White Flint | Roadway Modification | propose layby on Woodglen Drive extended | Conditional Approval | restricted for "no parking any time" |  | 2016-05-05
2011-12-19 | 2012-05-31 | 120120080 | Shady Grove Station |  | Request to have Master Planned roads “F,” “I,” and “J” be privately owned and maintained | Conditional approval recommendation (to planning board) | subject to a recorded perpetual Public Access Easement document & other details |  | 2012-06-13 | plan review comments letter to P&P and applicants
2011-12-19 | 2012-05-31 | 120120080 | Shady Grove Station |  | Reservation of land for Crabbs Branch Way/Shady Grove Metro Access Road interchange | Conditional approval recommendation (to planning board) | subject to determining the interchange concept design, traffic controls, and reservation area prior to approval of a Site Plan or 1st record plat for the east side of site |  | 2012-06-13 | plan review comments letter to P&P and applicants
2011-12-19 | 2012-05-31 | 120120080 | Shady Grove Station | SWM | Stormwater Management Measures in the rights-of-way on Crabbs Branch Way | Conditional Approval | of MSHA flume inlets and water quality/bio-swales on closed section road |  | 2012-06-13 | plan review comments letter to P&P and applicants
2011-12-19 | 2012-05-31 | 120120080 | Shady Grove Station | SWM | Stormwater Management Measures in the rights-of-way on Crabbs Branch Way | Denied | of request to install raised curbs on each side of the micro-bioretention facilities due to safety and liability concerns |  | 2012-06-13 | plan review comments letter to P&P and applicants
2011-12-19 | 2012-05-31 | 120120080 | Shady Grove Station | SWM | Proposal to provide stormwater management measures within the median for Crabbs Branch Way | Denied | due to concerns over traffic safety and operations |  | 2012-06-13 | plan review comments letter to P&P and applicants
2016-03-10 | 2016-05-17 | 120160270 | Sligo ArtSpace | Driveway Spacing | Applicant requested for a waiver of less than 100-ft separation between the proposed driveway entrance and and the intersection of Grove Street and Sligo Avenue. The applicant proposed to rtain the existing easternmost access point on Sligo Avenue. | Conditional Approval |  |  | 2016-06-10 | Design Exception and Preliminary Plan Letter
2016-03-10 | 2016-05-17 | 120160270 | Sligo ArtSpace | Modification to Context Sensitive Standard | Applicant requested to modify standard detail MC-2005.01 along Sligo Avenue. | Conditional Approval
2016-03-10 | 2016-05-17 | 120160270 | Sligo ArtSpace | Modification to Context Sensitive Standard | Applicant requested to retain existing pavement and widen the existing sidewalk behind the curb to 5.5 ft with the existing poles to remain. | Conditional approval recommendation (to planning board) | MCDOT recommended relocating the poles or relocating the curb two feet reducing the travel lane to get enough separation between the pole and travel lanes.
2015-05-04 |  | 120150200 | St.Elmo | Driveway Spacing | waiver from 100' tangent | Conditional Approval |  |  | 2015-08-11 | plan review letter to P&P and applicants
2012-10-15 | 2012-11-27 | 120130020 | Studio Plaza |  | Reduction in the number of off-street truck loading spaces [from that required by Executive Branch policy] | Conditional Approval | subject to execution and recordation of a County-approved Restricted Access Easement which establishes the applicability, maintenance, and operations of the coordinated on-site management for the jointly used loading docks and allowing access to dumpsters by the businesses on the opposite side of Mayor Lane |  | 2013-02-01 | plan review letter to P&P and applicants
2012-10-15 | 2012-11-27 | 120130020 | Studio Plaza | Driveway Spacing | Proposed driveway locations and reduced spacing [per DTEO policy] | Conditional Approval | in consideration of CBD location and decision to restrict Mayor Lane to one-way northbound movements |  | 2013-02-01 | plan review letter to P&P and applicants
2012-10-15 | 2012-11-27 | 120130020 | Studio Plaza |  | Private garage entrance location on new private street | Conditional Approval | since the opposite side alley only serves as a service access to the rear of an existing building |  | 2013-02-01 | plan review letter to P&P and applicants
2012-10-15 | 2012-11-27 | 120130020 | Studio Plaza |  | Reduced curb return radii (from 30’ DOT policy) | Conditional Approval | following review of the consultant’s turning movement diagrams |  | 2013-02-01 | plan review letter to P&P and applicants
2012-10-15 | 2012-11-27 | 120130020 | Studio Plaza | Sight Distance | Reduced sight distances requirements (from DOT policy) | Conditional Approval | of 150’ minimum on a business district street – in consideration of the CBD location |  | 2013-02-01 | plan review letter to P&P and applicants
2012-07-09 |  | 120120240 | suburban hospital | Roadway Modification | reduce maintenance shelf to provide 5 foot wide sidewalk | conditional approval |  |  | 2013-03-28 | prelim plan letter
2012-07-09 |  | 120120240 | suburban hospital | Roadway Modification | install 6-foot wide grass panel | Conditional approval recommendation (to planning board) | consistent with context sensitive road design standards |  | 2013-03-28 | prelim plan letter
2012-07-09 |  | 120120240 | suburban hospital | Roadway Modification | reduce tree panel to 2 feet | denial recommendation (to planning board) | result in maintenance issues; |  | 2013-03-28 | prelim plan letter
2013-07-09 |  | 120120240 | suburban hospital | Roadway Modification | reduced lane widths to 10 feet including curb lanes for additional turn lanes | denial recommendation (to planning board) | see preliminary plan letter |  | 2013-03-28 | prelim plan letter
2013-07-09 |  | 120120240 | suburban hospital | Roadway Modification | 6 foot wide curbed island in center or McKinley Street, per BOA approval, with a crosswalk pass-through | denial recommendation (to planning board) | see preliminary plan letter |  | 2013-03-28 | prelim plan letter
2013-07-09 |  | 120120240 | suburban hospital | signs | monumental sign to identify Huntington Terrace Subdivision in ROW | denial recommendation (to planning board) | located too close to roadway |  | 2013-03-28 | prelim plan letter
2013-07-09 |  | 120120240 | suburban hospital | signs | directional signs in the ROW | denial recommendation (to planning board) | sight distance issue |  | 2013-03-28 | prelim plan letter
2013-07-09 |  | 120120240 | suburban hospital | Driveway Spacing | waiver from 100' tangent | conditional approval | space limitations and proposed physical channelization measures |  | 2013-03-28 | prelim plan letter
2016-08-22 |  | 320170030 | The Claiborne | Driveway Spacing |  | Conditional Approval | waive DE requirement | prior precedent in the CBD | 2016-08-18 | in sketch plan letter
2012-09-06 |  | 82005003C | Westfield Montgomery Mall |  | Amend permit and pond requirement @ record plat for pendingLimited Site Plan amendment [to delay construction of ultimate roadway improvements (and relocated Transit Center) until the time of mall redevelopment] | Conditional Approval | subject to execution of a Public Improvements Agreement with the Department of Permitting Services (which provides guaranteed delivery dates for the required public improvements) |  | 2012-09-27 | email to DPS, P&P, and applicants
2015-11-13 |  | 120160060 | Wheaton Woods | Roadway Modification | Roadway cross section | Conditional Approval |  |  | 2015-11-30
2016-07-11 |  | 120160290 | WMAL | Roadway Modification | Renita Lane modified - to reduce the paving, ROW and removal of sidewalk | conditional approval | no parking; environmental issues; no connection to another sidewalk; Bill 34-16 |  | 2017-05-02 | Plan review letter to P&P and applicants
2011-02-28 |  | 92009001A 12009014A | Woodmont Central Phases 1A, 1B & 2 | other | Request to remove existing metered parking spaces to create a drop-off area for the project on Auburn Avenue near the intersection with Rugby Avenue | Denied |  |  | 2011-04-01 | 11 amended plan review comments letter to P&P and applicant
2011-11-28 | 2012-01-20 | 12007020B | Woodmont/7200 |  | Modified typical section on Bethesda Avenue for master planned shared use path between Woodmont Avenue and Wisconsin Avenue (MD 355) | Conditional Approval | to locate the path within the existing northern curblane, separated from the travel lane by a curb |  | 2012-03-23 | plan review letter to P&P and applicants
2011-11-28 | 2012-01-20 | 12007020B | Woodmont/7200 | Driveway Spacing | Proposed driveway locations and reduced spacing [per DTEO policy] | Conditional Approval | in consideration of CBD location |  | 2012-03-23 | plan review letter to P&P and applicants
2011-11-28 | 2012-01-20 | 12007020B | Woodmont/7200 |  | Reduction in the number of off-street truck loading spaces [from that required by Executive Branch policy] | Conditional Approval | subject to execution and recordation of a County-approved Restricted Access Easement which establishes the applicability, maintenance, and operations of the coordinated on-site management for the jointly used loading docks and requirement that truck movements must be made head-in, head-out (no back-in movement maneuvers across the shared use path) |  | 2012-03-23 | plan review letter to P&P and applicants
2011-11-28 | 2012-01-20 | 12007020B | Woodmont/7200 |  | Amenity space in the Bethesda Avenue right-of-way | Conditional Approval | subject to execution and recordation of Maintenance & Liability Agreement |  | 2012-03-23 | plan review letter to P&P and applicants
2011-11-28 | 2012-01-20 | 12007020B | Woodmont/7200 |  | Right-of-way truncation on the northwest corner of the intersection of Bethesda Avenue & Wisconsin Avenue (MD 355) | Denied | Recommended denial by the Planning Board in consideration of the pending pedestrian/bicycle crossing study at that intersection |  | 2012-03-23 | plan review letter to P&P and applicants
2011-11-28 | 2012-01-20 | 12007020B | Woodmont/7200 |  | Existing and previously approved electric vaults to remain in the right-of-way | Conditional Approval | in consideration of CBD location & subject to providing 16’ [per Design Exception document] clear pedestrian path |  | 2012-03-23 | plan review letter to P&P and applicants
2011-11-28 | 2012-01-20 | 12007020B | Woodmont/7200 |  | Width of lanes on Bethesda Avenue | Conditional Approval | to reduce the travel lane widths to 10’-11’ in consideration of the CBD location, multi-modal master plan requirements, limited right-of-way, etc. |  | 2012-03-23 | plan review letter to P&P and applicants
2016-09-26 |  | 120160330 | Wright Property | Roadway Modification | Roadway cross section | Conditional Approval |  |  | 2016-12-02 | plan review letter to P&P and applicants
2016-09-26 |  | 120160330 | Wright Property | Residential Road Intersection | Replacement of Residential Road Intersection (MC-220.01) with the Fire and Rescue Service approved driveway entrance. | Conditional Approval |  |  | 2016-12-02 | plan review letter to P&P and applicants

## Type
SWM
Sidewalk
Sight Distance
signs
Roadway Modification
Radii
Loading
other
Driveway Spacing
Residential Road Intersection

## Decision
Denied
denial recommendation (to planning board)
Conditional Approval
Conditional approval recommendation (to planning board)
Median Break